## issues (1)
ref | subject | description | milestone | owner | owner_full_name | assigned_to | assigned_to_full_name | status | severity | priority | type | is_closed | attachments | external_reference | tags
114 | get latest version deployed - resolve build conflicts |  |  | bschwetz-1 | Billie |  |  | Closed | Critical | High | Bug | TRUE | 0
115 | Update color of corn, hard to see. Add to food label | add to food label and change color as it was hard to see. |  | bschwetz-1 | Billie |  |  | Closed | Normal | Normal | Enhancement | TRUE | 0 |  | #72
116 | Add header to modal window for enhancement report |  |  | bschwetz-1 | Billie |  |  | Closed | Normal | Normal | Enhancement | TRUE | 0
198 | GUI changes based on Stakeholder comments from Sprint 5 Review | Add headers below FDA Data that says "Trend Data" move map cards below other cards Add Header for "Top News" Update about text with links, remove the more in about section Link integrity one text to integrity one site update mascot to crossed arm add FDA to top part Link home to page refresh |  | bschwetz-1 | Billie |  |  | Closed | Normal | Normal | Bug | TRUE | 0 |  | sprint 5 demo
199 | Affected Areas toggle not working | icons aren't refreshing and the affected areas show as default |  | bschwetz-1 | Billie |  |  | Closed | Normal | Normal | Bug | TRUE | 0 |  | sprint 5 demo
200 | The system does not display "Good news, no Affected areas!" when searching for recalls as per the requirement- user story 45 |  |  | dkamal1 | David Kamal |  |  | New | Normal | Normal | Bug | FALSE | 0
206 | Related Defender frames do not display 'Nothing Trending on Google!' when Google trends have no trends response- 33 |  |  | bschwetz-1 | Billie |  |  | New | Normal | Normal | Bug | FALSE | 0
207 | Would like to see affected area colored similar to the color of the icon. |  |  | bschwetz-1 | Billie |  |  | Closed | Normal | Normal | Bug | TRUE | 0 |  | uat comment
208 | Would like to see the date format in the grid display as MM/DD/YYY |  |  | bschwetz-1 | Billie |  |  | Closed | Normal | Normal | Bug | TRUE | 0 |  | uat comment
229 | Map pulling logic can be better/faster | Known issue with the way the map is loading. Would like to put in logic to speed this up |  | bschwetz-1 | Billie |  |  | Needs Info | Normal | Normal | Question | FALSE | 0 |  | raise to po