## tasks (1)
ref | subject | description | user_story | milestone | owner | owner_full_name | assigned_to | assigned_to_full_name | status | is_iocaine | is_closed | us_order | taskboard_order | attachments | external_reference | tags | Hours
2 | Identify Bubble API | Identify which Leaflet/ESRI API to use for bubble volume overlay. | 6 | Sprint 0 | bschwetz-1 | Billie | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 0 | 0
4 | Research Topsy / Twitter / More | Determine if good APIs exist and that they have fields we want. Topsy costs $$, the other one is just for your own metrics, falling back to Twitter API only (for now) | 5 | Sprint 0 | bschwetz-1 | Billie | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 0 | 0
9 | Identify which API calls to use | Identify which calls to use against selected API | 6 | Sprint 0 | eahollin | Ed Hollingsworth | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 1 | 0
10 | Research in PNSI data can be related to enforcement records |  | 8 | Sprint 0 | swinkler149 | Steve Winkler | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 2 | 0
11 | Research in CDC data can be associated with enforcement data |  | 8 | Sprint 0 | swinkler149 | Steve Winkler |  |  | Closed | FALSE | TRUE | 1 | 0 | 0
12 | Developer IDE Setup |  | 7 | Sprint 0 | swinkler149 | Steve Winkler | swinkler149 | Steve Winkler | Closed | FALSE | TRUE | 1 | 2 | 0
13 | Generate AS EC2 Instance for Development Server |  | 7 | Sprint 0 | swinkler149 | Steve Winkler | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 7 | 0
14 | Connect Developers to new EC2 instance |  | 7 | Sprint 0 | swinkler149 | Steve Winkler | swinkler149 | Steve Winkler | Closed | FALSE | TRUE | 1 | 10 | 0
15 | Load Yeoman framework on development server |  | 7 | Sprint 0 | swinkler149 | Steve Winkler | swinkler149 | Steve Winkler | Closed | FALSE | TRUE | 1 | 8 | 0
16 | Generate Angular Fullstack template for Application |  | 7 | Sprint 0 | swinkler149 | Steve Winkler | swinkler149 | Steve Winkler | Closed | FALSE | TRUE | 1 | 11 | 0
17 | Initial GitHub commit of application template |  | 7 | Sprint 0 | swinkler149 | Steve Winkler | swinkler149 | Steve Winkler | Closed | FALSE | TRUE | 1 | 6 | 0
18 | Extract/Sync checked in baseline to developer images |  | 7 | Sprint 0 | swinkler149 | Steve Winkler | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 3 | 0
19 | Research TravisCI/AWS Code Deploy |  | 7 | Sprint 0 | ferrx | steven ferrell | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 9 | 0
20 | Create Sprint 0 test plan / test cases | Create test plan and test cases to validate Sprint 0. | 7 | Sprint 0 | tonypetruccelli | Tony Petruccelli | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 4 | 0
21 | Configure Selenium IDE | Configure Selenium IDE for automated testing. | 7 | Sprint 0 | tonypetruccelli | Tony Petruccelli | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 5 | 0
22 | Execute Sprint 0 test cases | Execute test cases for Sprint 0 | 7 | Sprint 0 | tonypetruccelli | Tony Petruccelli | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 0 | 0
23 | Research the Google Trends API |  | 1 | Sprint 0 | ferrx | steven ferrell | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 0 | 0
24 | Install Ruby and setup Travis on server |  | 7 | Sprint 0 | ferrx | steven ferrell | swinkler149 | Steve Winkler | Closed | FALSE | TRUE | 1 | 1 | 0
39 | Create AMI from MEAN baseline instance |  | 7 | Sprint 0 | eahollin | Ed Hollingsworth | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 13 | 0
40 | Create 3 Developer Instances from Custom AMI |  | 7 | Sprint 0 | eahollin | Ed Hollingsworth | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 12 | 0
41 | USDA |  | 8 | Sprint 0 | ferrx | steven ferrell | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 4 | 0
42 | CPSC |  | 8 | Sprint 0 | ferrx | steven ferrell | tonypetruccelli | Tony Petruccelli | Closed | FALSE | TRUE | 1 | 3 | 0
43 | State Health |  | 8 | Sprint 0 | ferrx | steven ferrell | tonypetruccelli | Tony Petruccelli | Closed | FALSE | TRUE | 1 | 1 | 0
46 | Unit test written |  | 26 | Sprint 2 | bschwetz-1 | Billie | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 20 | 0 |  | testqa
47 | code review complete |  | 26 | Sprint 2 | bschwetz-1 | Billie |  |  | Closed | FALSE | TRUE | 1 | 9 | 0 |  | dev
48 | update reqs docs/backlog itesm |  | 26 | Sprint 2 | bschwetz-1 | Billie |  |  | Closed | FALSE | TRUE | 1 | 19 | 0 |  | analyst
49 | Generate server-side model code and controller |  | 26 | Sprint 2 | eahollin | Ed Hollingsworth | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 14 | 0 |  | dev
50 | Generate client-side controller code |  | 26 | Sprint 2 | eahollin | Ed Hollingsworth | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 21 | 0 |  | dev
51 | Customize server-side controller to query data |  | 26 | Sprint 2 | eahollin | Ed Hollingsworth | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 11 | 0 |  | dev
52 | Customize client-side controller to communicate with server-side controller | part of pagination - moved to a new user story | 26 | Sprint 2 | eahollin | Ed Hollingsworth | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 3 | 0 |  | dev
53 | Create user interface using grid control |  | 26 | Sprint 2 | eahollin | Ed Hollingsworth | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 22 | 0 |  | dev
54 | Customize client-side controller to interact with UI layer |  | 26 | Sprint 2 | eahollin | Ed Hollingsworth | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 23 | 0 |  | dev
55 | Research javascript plugin for Selenium | We need to find a way for the IDE to generate Javascript rather than Java | 26 | Sprint 2 | dkamal1 | David Kamal | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 7 | 0
56 | Modify query to use search criteria |  | 28 | Sprint 4 | eahollin | Ed Hollingsworth | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 0 | 0 |  | dev
57 | Modify UI to allow entry of search criteria |  | 28 | Sprint 4 | eahollin | Ed Hollingsworth | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 7 | 0 |  | dev
58 | Complete CI registration |  | 26 | Sprint 2 | eahollin | Ed Hollingsworth | swinkler149 | Steve Winkler | Closed | FALSE | TRUE | 1 | 0 | 0 |  | dev
59 | Enter CI license info. on Server |  | 26 | Sprint 2 | eahollin | Ed Hollingsworth | swinkler149 | Steve Winkler | Closed | FALSE | TRUE | 1 | 13 | 0 |  | dev
60 | Configure CI on Travis-CI website |  | 26 | Sprint 2 | eahollin | Ed Hollingsworth | swinkler149 | Steve Winkler | Closed | FALSE | TRUE | 1 | 2 | 0 |  | dev
61 | Add UI functionality to select one or more types |  | 34 |  | eahollin | Ed Hollingsworth | ferrx | steven ferrell | In progress | FALSE | FALSE | 1 | 0 | 0 |  | dev
62 | Modify query to incorporate type criteria |  | 34 |  | eahollin | Ed Hollingsworth | eahollin | Ed Hollingsworth | New | FALSE | FALSE | 1 | 0 | 0 |  | dev
63 | Complete research of AWS monitoring capability |  | 26 | Sprint 2 | eahollin | Ed Hollingsworth | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 15 | 0 |  | dev
64 | Implement standard error server response |  | 26 | Sprint 2 | eahollin | Ed Hollingsworth | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 12 | 0 |  | dev
65 | Implement standard client error display |  | 26 | Sprint 2 | eahollin | Ed Hollingsworth | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 18 | 0 |  | dev
66 | Standardize Unit Testing approach |  | 26 | Sprint 2 | eahollin | Ed Hollingsworth | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 16 | 0 |  | dev
67 | Implement basic continuous monitoring via AWS |  | 26 | Sprint 2 | eahollin | Ed Hollingsworth | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 6 | 0 |  | dev
69 | Download and Set Up OpenSource Test Management Tool |  | 26 | Sprint 2 | dkamal1 | David Kamal | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 17 | 0
70 | Create Manual Funtional Test Case for acceptance Criteria |  | 26 | Sprint 2 | dkamal1 | David Kamal | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 8 | 0
71 | Add UI Functioanlity for More button |  | 25 | Sprint 3 | ferrx | steven ferrell | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 1 | 0 |  | dev
73 | Execute Functional Test Case |  | 26 | Sprint 2 | dkamal1 | David Kamal | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 1 | 0
74 | Create Functional Test Case Scenario |  | 34 |  | dkamal1 | David Kamal | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 0 | 0
75 | Execute Functional Test Case |  | 34 |  | dkamal1 | David Kamal |  |  | New | FALSE | FALSE | 1 | 1 | 0
76 | Execute Functional Test Case |  | 26 | Sprint 2 | dkamal1 | David Kamal | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 5 | 0 |  | testqa
77 | Create Functional Test Scenario |  | 25 | Sprint 3 | dkamal1 | David Kamal | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 0 | 0 |  | testqa
78 | Execute Functional Test Case |  | 25 | Sprint 3 | dkamal1 | David Kamal | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 2 | 0 |  | testqa
79 | Create Functional Test Scenario |  | 72 | Sprint 3 | dkamal1 | David Kamal | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 0 | 0 |  | testqa
80 | Execute Functional Test Case |  | 72 | Sprint 3 | dkamal1 | David Kamal | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 3 | 0 |  | testqa
84 | Create UI Esri Code for map |  | 72 | Sprint 3 | ferrx | steven ferrell | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 6 | 0 |  | dev | 20 m
85 | Create UI functionality to show map on page |  | 72 | Sprint 3 | ferrx | steven ferrell | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 1 | 0 |  | dev
86 | Pagination for grid | moving to another story | 26 | Sprint 2 | ferrx | steven ferrell |  |  | Closed | TRUE | TRUE | 1 | 10 | 0
87 | Incorporate dynamic date for previous month |  | 26 | Sprint 2 | eahollin | Ed Hollingsworth | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 4 | 0 |  | dev
89 | add data to report |  | 25 | Sprint 3 | bschwetz-1 | Billie | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 3 | 0 |  | dev
91 | create unit test |  | 72 | Sprint 3 | bschwetz-1 | Billie | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 4 | 0 |  | dev
92 | code review |  | 72 | Sprint 3 | bschwetz-1 | Billie | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 2 | 0 |  | dev
93 | create unit test |  | 25 | Sprint 3 | bschwetz-1 | Billie |  |  | Closed | FALSE | TRUE | 1 | 5 | 0
94 | code review |  | 25 | Sprint 3 | bschwetz-1 | Billie | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 4 | 0
95 | implement design features |  | 25 | Sprint 3 | bschwetz-1 | Billie |  |  | Closed | FALSE | TRUE | 1 | 7 | 0
96 | create unit test |  | 30 | Sprint 4 | bschwetz-1 | Billie | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 7 | 0 |  | dev
97 | conduct code review |  | 30 | Sprint 4 | bschwetz-1 | Billie | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 3 | 0
98 | Create funcational test scripts |  | 30 | Sprint 4 | bschwetz-1 | Billie | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 0 | 0
99 | set up custom icon markers |  | 72 | Sprint 3 | eahollin | Ed Hollingsworth | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 5 | 0 |  | dev
100 | Execute functional test scripts |  | 30 | Sprint 4 | bschwetz-1 | Billie | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 2 | 0
101 | set up geocoder to find recall locations |  | 72 | Sprint 3 | eahollin | Ed Hollingsworth | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 3 | 0 |  | dev
102 | create feature layer based on locations and add to map |  | 30 | Sprint 4 | eahollin | Ed Hollingsworth | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 1 | 0 |  | dev
103 | identify logic for suppressing multiple markers at a single location |  | 30 | Sprint 4 | eahollin | Ed Hollingsworth | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 4 | 0 |  | dev
105 | update SRS |  | 104 | Sprint 3 | bschwetz-1 | Billie | bschwetz-1 | Billie | Closed | FALSE | TRUE | 1 | 0 | 0 |  | documentation
106 | create High-Level Design document |  | 104 | Sprint 3 | bschwetz-1 | Billie | tonypetruccelli | Tony Petruccelli | Closed | FALSE | TRUE | 1 | 1 | 0 |  | documentation
107 | Modify refiner ui components |  | 90 | Sprint 4 | ferrx | steven ferrell | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 0 | 0
108 | Add big query text to UI |  | 90 | Sprint 4 | ferrx | steven ferrell | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 3 | 0
109 | Fix Bootstrap theme / Grunt issue |  | 25 | Sprint 3 | ferrx | steven ferrell | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 6 | 0
110 | review aws monitoring and system monitoring and provide update | Continuous monitoring metrics will be performed through Amazon cloudwatch. A combination of out of the box metrics and custom application metrics will be continuously monitored. Application metrics which will be added include: Application Up/Down status (alarm when down) Number of page hits Number of errors detected Average Page Get Time (alarm when exceeds threshold) | 104 | Sprint 3 | bschwetz-1 | Billie | swinkler149 | Steve Winkler | Closed | FALSE | TRUE | 1 | 2 | 0
120 | add design components |  | 28 | Sprint 4 | bschwetz-1 | Billie |  |  | Closed | FALSE | TRUE | 1 | 6 | 0
121 | unit test |  | 28 | Sprint 4 | bschwetz-1 | Billie |  |  | Closed | FALSE | TRUE | 1 | 4 | 0
122 | code review |  | 28 | Sprint 4 | bschwetz-1 | Billie | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 3 | 0 |  | dev
123 | Create Functional Test Scenario |  | 28 | Sprint 4 | bschwetz-1 | Billie | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 8 | 0
124 | Execute Functional Test Case |  | 28 | Sprint 4 | bschwetz-1 | Billie | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 2 | 0
125 | update documentation with any applicable changes |  | 28 | Sprint 4 | bschwetz-1 | Billie |  |  | Closed | FALSE | TRUE | 1 | 1 | 0 |  | documentation
126 | add helper text | this was changed to randomizer | 28 | Sprint 4 | bschwetz-1 | Billie | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 5 | 0
127 | Setup controller for binding to search term query |  | 28 | Sprint 4 | ferrx | steven ferrell | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 9 | 0
128 | Swap in corn images |  | 117 | Sprint 4 | eahollin | Ed Hollingsworth | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 0 | 0 |  | dev
129 | update food label to corn color |  | 117 | Sprint 4 | eahollin | Ed Hollingsworth | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 1 | 0 |  | dev
130 | Enable morgan application logging in application |  | 112 | Sprint 5 | swinkler149 | Steve Winkler | swinkler149 | Steve Winkler | Closed | FALSE | TRUE | 1 | 3 | 0
131 | Connect to AWS metrics console for production server |  | 112 | Sprint 5 | swinkler149 | Steve Winkler | swinkler149 | Steve Winkler | Closed | FALSE | TRUE | 1 | 0 | 0
132 | Add AWS out of the box metrics/alarms for production server |  | 112 | Sprint 5 | swinkler149 | Steve Winkler | swinkler149 | Steve Winkler | Closed | FALSE | TRUE | 1 | 1 | 0
133 | Add custom metrics for AWS monitoring |  | 112 | Sprint 5 | swinkler149 | Steve Winkler | swinkler149 | Steve Winkler | Closed | FALSE | TRUE | 1 | 2 | 0
134 | add header |  | 119 | Sprint 4 | bschwetz-1 | Billie | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 0 | 0
135 | test |  | 119 | Sprint 4 | bschwetz-1 | Billie |  |  | Closed | FALSE | TRUE | 1 | 1 | 0
136 | add api code for SEARCH param |  | 90 | Sprint 4 | ferrx | steven ferrell | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 6 | 0
137 | Create Functional Test Scenario |  | 90 | Sprint 4 | bschwetz-1 | Billie | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 1 | 0 |  | testqa
138 | unit test |  | 90 | Sprint 4 | bschwetz-1 | Billie | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 4 | 0
139 | code review |  | 90 | Sprint 4 | bschwetz-1 | Billie | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 2 | 0 |  | dev
140 | Execute Test Case |  | 90 | Sprint 4 | bschwetz-1 | Billie | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 5 | 0 |  | testqa
141 | Use module scope var for resultset |  | 30 | Sprint 4 | eahollin | Ed Hollingsworth | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 6 | 0 |  | dev
142 | Move map refresh code into function |  | 30 | Sprint 4 | eahollin | Ed Hollingsworth | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 5 | 0 |  | dev
144 | write unit test |  | 111 | Sprint 5 | bschwetz-1 | Billie | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 3 | 0
146 | Create Location parsing |  | 45 | Sprint 5 | ferrx | steven ferrell | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 4 | 0 |  |  | 0.5
147 | Retrieve location data from module scope |  | 45 | Sprint 5 | eahollin | Ed Hollingsworth | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 6 | 0 |  | dev
148 | Geocode dictionary of locations |  | 45 | Sprint 5 | eahollin | Ed Hollingsworth | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 5 | 0 |  | dev
149 | create unit test |  | 45 | Sprint 5 | bschwetz-1 | Billie | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 2 | 0 |  | dev
150 | code review |  | 45 | Sprint 5 | bschwetz-1 | Billie | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 1 | 0 |  | dev
151 | Create Functional Test Case |  | 45 | Sprint 5 | bschwetz-1 | Billie | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 9 | 0 |  | testqa
152 | Switch to drug icon when drug recalls are selected |  | 82 | Sprint 5 | eahollin | Ed Hollingsworth | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 4 | 0 |  | dev
153 | Verify location naming conventions for parsing |  | 45 | Sprint 5 | ferrx | steven ferrell | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 0 | 0 |  |  | 0.5
154 | Create sized bubbles for each area based on value |  | 45 | Sprint 5 | eahollin | Ed Hollingsworth | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 3 | 0 |  | dev
155 | Create separate API call for Device search |  | 83 | Sprint 5 | eahollin | Ed Hollingsworth | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 0 | 0 |  | dev
156 | Create separate API call for Drug search |  | 82 | Sprint 5 | eahollin | Ed Hollingsworth | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 2 | 0 |  | dev
157 | Adjust styles/cols for better fit and look of cols |  | 33 | Sprint 5 | ferrx | steven ferrell | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 0 | 0
158 | Incorporate Drug image |  | 82 | Sprint 5 | eahollin | Ed Hollingsworth |  |  | Closed | FALSE | TRUE | 1 | 5 | 0 |  | dev
159 | Incorporatae Device image |  | 83 | Sprint 5 | eahollin | Ed Hollingsworth |  |  | Closed | FALSE | TRUE | 1 | 5 | 0 |  | dev
160 | create unit test |  | 82 | Sprint 5 | bschwetz-1 | Billie | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 8 | 0
161 | code review |  | 82 | Sprint 5 | bschwetz-1 | Billie | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 3 | 0 |  | dev
162 | update docs |  | 82 | Sprint 5 | bschwetz-1 | Billie |  |  | Closed | FALSE | TRUE | 1 | 9 | 0
163 | C |  | 82 | Sprint 5 | bschwetz-1 | Billie |  |  | Closed | FALSE | TRUE | 1 | 7 | 0
164 | Execute Test Case |  | 82 | Sprint 5 | bschwetz-1 | Billie | dkamal1 | David Kamal | In progress | FALSE | FALSE | 1 | 0 | 0 |  | testqa
165 | Create additional client side handler |  | 82 | Sprint 5 | ferrx | steven ferrell | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 0 | 0 |  |  | 1
166 | Modify dependencies such as Randomizer list |  | 82 | Sprint 5 | ferrx | steven ferrell | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 10 | 0 |  |  | 0.5
167 | unit test |  | 33 | Sprint 5 | bschwetz-1 | Billie |  |  | Closed | FALSE | TRUE | 1 | 3 | 0
168 | code review |  | 33 | Sprint 5 | bschwetz-1 | Billie |  |  | Closed | FALSE | TRUE | 1 | 5 | 0
169 | Create Functional Test Scenario |  | 33 | Sprint 5 | bschwetz-1 | Billie | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 4 | 0 |  | testqa
170 | Execute Test Case |  | 33 | Sprint 5 | bschwetz-1 | Billie | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 2 | 0 |  | testqa
171 | update docs |  | 33 | Sprint 5 | bschwetz-1 | Billie |  |  | Closed | FALSE | TRUE | 1 | 1 | 0
172 | Create dynamic search term binding |  | 188 | Sprint 5 | ferrx | steven ferrell | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 1 | 0
173 | Create Functional Test Scenario |  | 111 | Sprint 5 | bschwetz-1 | Billie | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 1 | 0 |  | testqa
174 | Execute Test Case |  | 111 | Sprint 5 | bschwetz-1 | Billie | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 0 | 0 |  | testqa
175 | update docs |  | 111 | Sprint 5 | bschwetz-1 | Billie |  |  | Closed | FALSE | TRUE | 1 | 2 | 0
176 | create unit test |  | 83 | Sprint 5 | bschwetz-1 | Billie | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 2 | 0
177 | code review |  | 83 | Sprint 5 | bschwetz-1 | Billie |  |  | Closed | FALSE | TRUE | 1 | 4 | 0
178 | update docs |  | 83 | Sprint 5 | bschwetz-1 | Billie |  |  | Closed | FALSE | TRUE | 1 | 7 | 0
179 | Create Functional Test Case |  | 83 | Sprint 5 | bschwetz-1 | Billie | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 6 | 0 |  | testqa
180 | Execute Test Case |  | 83 | Sprint 5 | bschwetz-1 | Billie | dkamal1 | David Kamal | In progress | FALSE | FALSE | 1 | 0 | 0 |  | testqa
181 | add content with correct style |  | 111 | Sprint 5 | ferrx | steven ferrell | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 0 | 0
182 | Install aws CLI on production server |  | 143 | Sprint 5 | swinkler149 | Steve Winkler | swinkler149 | Steve Winkler | Closed | FALSE | TRUE | 1 | 0 | 0
183 | Register custom collected metrics into Amazon cloudworks via CLI calls |  | 143 | Sprint 5 | swinkler149 | Steve Winkler | swinkler149 | Steve Winkler | Closed | FALSE | TRUE | 1 | 1 | 0
184 | Create AWS alarms on custom metrics |  | 143 | Sprint 5 | swinkler149 | Steve Winkler | swinkler149 | Steve Winkler | Closed | FALSE | TRUE | 1 | 3 | 0
185 | Research other APIs |  | 188 | Sprint 5 | ferrx | steven ferrell | swinkler149 | Steve Winkler | Closed | FALSE | TRUE | 1 | 0 | 0
186 | Implement popup on icons |  | 45 | Sprint 5 | eahollin | Ed Hollingsworth | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 7 | 0 |  | dev
187 | Implement auto-resize based on featurelayer boundary |  | 45 | Sprint 5 | eahollin | Ed Hollingsworth | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 8 | 0 |  | dev
189 | unit test |  | 188 | Sprint 5 | bschwetz-1 | Billie |  |  | Closed | FALSE | TRUE | 1 | 2 | 0
190 | code review |  | 188 | Sprint 5 | bschwetz-1 | Billie |  |  | Closed | FALSE | TRUE | 1 | 3 | 0
191 | Create Functional Test Case |  | 188 | Sprint 5 | bschwetz-1 | Billie | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 5 | 0 |  | testqa
192 | Execute Test Case |  | 188 | Sprint 5 | bschwetz-1 | Billie | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 0 | 0 |  | testqa
193 | Execute Functional Test Case |  | 45 | Sprint 5 | dkamal1 | David Kamal | dkamal1 | David Kamal | In progress | FALSE | FALSE | 1 | 2 | 0 |  | testqa
194 | Create Functional Test Scenario |  | 82 | Sprint 5 | dkamal1 | David Kamal | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 6 | 0 |  | testqa
195 | integrate api |  | 188 | Sprint 5 | bschwetz-1 | Billie | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 6 | 0 |  | dev
196 | Switch to device icon for device recall searches |  | 83 | Sprint 5 | eahollin | Ed Hollingsworth | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 3 | 0 |  | dev
197 | Check in continuous integration and continuous monitoring scripts (external to app build) |  | 143 | Sprint 5 | swinkler149 | Steve Winkler | swinkler149 | Steve Winkler | Closed | FALSE | TRUE | 1 | 2 | 0
221 | implement update |  | 212 | Sprint 6 - Release Sprint | bschwetz-1 | Billie | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 2 | 0 |  | dev
222 | update unit tests |  | 212 | Sprint 6 - Release Sprint | bschwetz-1 | Billie | eahollin | Ed Hollingsworth | Closed | FALSE | TRUE | 1 | 1 | 0 |  | dev
223 | update docs |  | 212 | Sprint 6 - Release Sprint | bschwetz-1 | Billie |  |  | Closed | FALSE | TRUE | 1 | 1 | 0
224 | Create Functional Test Case |  | 212 | Sprint 6 - Release Sprint | bschwetz-1 | Billie | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 0 | 0
225 | implement update |  | 211 | Sprint 6 - Release Sprint | bschwetz-1 | Billie | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 1 | 0
226 | update unit tests |  | 211 | Sprint 6 - Release Sprint | bschwetz-1 | Billie | ferrx | steven ferrell | Closed | FALSE | TRUE | 1 | 0 | 0
227 | update docs |  | 211 | Sprint 6 - Release Sprint | bschwetz-1 | Billie |  |  | Closed | FALSE | TRUE | 1 | 0 | 0
228 | test |  | 211 | Sprint 6 - Release Sprint | bschwetz-1 | Billie | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 1 | 0
232 | Execute Functional Test Case |  | 212 | Sprint 6 - Release Sprint | dkamal1 | David Kamal | dkamal1 | David Kamal | Closed | FALSE | TRUE | 1 | 1 | 0