## issues
ref | subject | description | owner_full_name | status | severity | priority | type | is_closed | tags
114 | get latest version deployed - resolve build conflicts |  | Billie | Closed | Critical | High | Bug | TRUE
115 | Update color of corn, hard to see. Add to food label | add to food label and change color as it was hard to see. | Billie | Closed | Normal | Normal | Enhancement | TRUE | #72
116 | Add header to modal window for enhancement report |  | Billie | Closed | Normal | Normal | Enhancement | TRUE
198 | GUI changes based on Stakeholder comments from Sprint 5 Review | Add headers below FDA Data that says "Trend Data" move map cards below other cards Add Header for "Top News" Update about text with links, remove the more in about section Link integrity one text to integrity one site update mascot to crossed arm add FDA to top part Link home to page refresh | Billie | Closed | Normal | Normal | Bug | TRUE | sprint 5 demo
199 | Affected Areas toggle not working | icons aren't refreshing and the affected areas show as default | Billie | Closed | Normal | Normal | Bug | TRUE | sprint 5 demo
200 | The system does not display "Good news, no Affected areas!" when searching for recalls as per the requirement- user story 45 |  | David | New | Normal | Normal | Bug | FALSE
206 | Related Defender frames do not display 'Nothing Trending on Google!' when Google trends have no trends response- 33 |  | Billie | Closed | Normal | Normal | Bug | TRUE
207 | Would like to see affected area colored similar to the color of the icon. |  | Billie | Closed | Normal | Normal | Bug | TRUE | uat comment
208 | Would like to see the date format in the grid display as MM/DD/YYY |  | Billie | Closed | Normal | Normal | Bug | TRUE | uat comment
229 | Map pulling logic can be better/faster | Known issue with the way the map is loading. Would like to put in logic to speed this up | Billie | Needs Info | Normal | Normal | Question | FALSE | raise to po
233 | Several recalls that appear in the default search results that have an initiation date of 2012 show up as recalls in the past 90 days. | There are several recalls that appear in the default search results that have an initiation date of 2012 that show up as recalls in the past 90 days. When I manually run the query for the last 90 days, I donâ€™t get these recalls. Was this query changed? I am running the following recalls query for food https://api.fda.gov/food/enforcement.json?search=report_date:[20150328+TO+20150628]&limit=100 Example of food recalls that appear on the page that are not returned by the 90 day query include Recall( #F-0283-2013 Recall Initiation Date 09/10/2012 Recalling Firm Spartan Central Kitchen) and Recall (#F-2448-2012 Recall Initiation Date 08/28/2012 Recalling Firm Sadie's Salads) | David | Closed | Normal | Normal | Bug | TRUE
234 | When no results are found during a recall search, the Top Regions section returns a browser error â€œThe Website Cannot display the Pageâ€ | When no results are found during a recall search, the Top Regions section returns a browser error â€œThe Website Cannot display the Pageâ€ | David | Closed | Normal | Normal | Bug | TRUE
235 | The mascot is not updated to cross armed as per the acceptance criteria | The mascot is not updated to cross armed as per the acceptance criteria | David | Closed | Normal | Normal | Bug | TRUE