## tasks
ref | subject | description | user_story | milestone | owner_full_name | assigned_to_full_name | status | is_iocaine | is_closed | us_order | taskboard_order | attachments | external_reference | tags | Hours
2 | Identify Bubble API | Identify which Leaflet/ESRI API to use for bubble volume overlay. | 6 | Sprint 0 | Billie | Ed | Closed | FALSE | TRUE | 1 | 0 | 0
4 | Research Topsy / Twitter / More | Determine if good APIs exist and that they have fields we want. Topsy costs $$, the other one is just for your own metrics, falling back to Twitter API only (for now) | 5 | Sprint 0 | Billie | Ed | Closed | FALSE | TRUE | 1 | 0 | 0
9 | Identify which API calls to use | Identify which calls to use against selected API | 6 | Sprint 0 | Ed | Ed | Closed | FALSE | TRUE | 1 | 1 | 0
10 | Research in PNSI data can be related to enforcement records |  | 8 | Sprint 0 | Steve | Steven | Closed | FALSE | TRUE | 1 | 2 | 0
11 | Research in CDC data can be associated with enforcement data |  | 8 | Sprint 0 | Steve |  | Closed | FALSE | TRUE | 1 | 0 | 0
12 | Developer IDE Setup |  | 7 | Sprint 0 | Steve | Steve | Closed | FALSE | TRUE | 1 | 2 | 0
13 | Generate AS EC2 Instance for Development Server |  | 7 | Sprint 0 | Steve | Ed | Closed | FALSE | TRUE | 1 | 7 | 0
14 | Connect Developers to new EC2 instance |  | 7 | Sprint 0 | Steve | Steve | Closed | FALSE | TRUE | 1 | 10 | 0
15 | Load Yeoman framework on development server |  | 7 | Sprint 0 | Steve | Steve | Closed | FALSE | TRUE | 1 | 8 | 0
16 | Generate Angular Fullstack template for Application |  | 7 | Sprint 0 | Steve | Steve | Closed | FALSE | TRUE | 1 | 11 | 0
17 | Initial GitHub commit of application template |  | 7 | Sprint 0 | Steve | Steve | Closed | FALSE | TRUE | 1 | 6 | 0
18 | Extract/Sync checked in baseline to developer images |  | 7 | Sprint 0 | Steve | Ed | Closed | FALSE | TRUE | 1 | 3 | 0
19 | Research TravisCI/AWS Code Deploy |  | 7 | Sprint 0 | Steven | Steven | Closed | FALSE | TRUE | 1 | 9 | 0
20 | Create Sprint 0 test plan / test cases | Create test plan and test cases to validate Sprint 0. | 7 | Sprint 0 | Tony | David | Closed | FALSE | TRUE | 1 | 4 | 0
21 | Configure Selenium IDE | Configure Selenium IDE for automated testing. | 7 | Sprint 0 | Tony | David | Closed | FALSE | TRUE | 1 | 5 | 0
22 | Execute Sprint 0 test cases | Execute test cases for Sprint 0 | 7 | Sprint 0 | Tony | David | Closed | FALSE | TRUE | 1 | 0 | 0
23 | Research the Google Trends API |  | 1 | Sprint 0 | Steven | Steven | Closed | FALSE | TRUE | 1 | 0 | 0
24 | Install Ruby and setup Travis on server |  | 7 | Sprint 0 | Steven | Steve | Closed | FALSE | TRUE | 1 | 1 | 0
39 | Create AMI from MEAN baseline instance |  | 7 | Sprint 0 | Ed | Ed | Closed | FALSE | TRUE | 1 | 13 | 0
40 | Create 3 Developer Instances from Custom AMI |  | 7 | Sprint 0 | Ed | Ed | Closed | FALSE | TRUE | 1 | 12 | 0
41 | USDA |  | 8 | Sprint 0 | Steven | Steven | Closed | FALSE | TRUE | 1 | 4 | 0
42 | CPSC |  | 8 | Sprint 0 | Steven | Tony | Closed | FALSE | TRUE | 1 | 3 | 0
43 | State Health |  | 8 | Sprint 0 | Steven | Tony | Closed | FALSE | TRUE | 1 | 1 | 0
46 | Unit test written |  | 26 | Sprint 2 | Billie | Steven | Closed | FALSE | TRUE | 1 | 20 | 0 |  | testqa
47 | code review complete |  | 26 | Sprint 2 | Billie |  | Closed | FALSE | TRUE | 1 | 9 | 0 |  | dev
48 | update reqs docs/backlog itesm |  | 26 | Sprint 2 | Billie |  | Closed | FALSE | TRUE | 1 | 19 | 0 |  | analyst
49 | Generate server-side model code and controller |  | 26 | Sprint 2 | Ed | Ed | Closed | FALSE | TRUE | 1 | 14 | 0 |  | dev
50 | Generate client-side controller code |  | 26 | Sprint 2 | Ed | Steven | Closed | FALSE | TRUE | 1 | 21 | 0 |  | dev
51 | Customize server-side controller to query data |  | 26 | Sprint 2 | Ed | Ed | Closed | FALSE | TRUE | 1 | 11 | 0 |  | dev
52 | Customize client-side controller to communicate with server-side controller | part of pagination - moved to a new user story | 26 | Sprint 2 | Ed | Steven | Closed | FALSE | TRUE | 1 | 3 | 0 |  | dev
53 | Create user interface using grid control |  | 26 | Sprint 2 | Ed | Steven | Closed | FALSE | TRUE | 1 | 22 | 0 |  | dev
54 | Customize client-side controller to interact with UI layer |  | 26 | Sprint 2 | Ed | Steven | Closed | FALSE | TRUE | 1 | 23 | 0 |  | dev
55 | Research javascript plugin for Selenium | We need to find a way for the IDE to generate Javascript rather than Java | 26 | Sprint 2 | David | David | Closed | FALSE | TRUE | 1 | 7 | 0
56 | Modify query to use search criteria |  | 28 | Sprint 4 | Ed | Steven | Closed | FALSE | TRUE | 1 | 0 | 0 |  | dev
57 | Modify UI to allow entry of search criteria |  | 28 | Sprint 4 | Ed | Steven | Closed | FALSE | TRUE | 1 | 7 | 0 |  | dev
58 | Complete CI registration |  | 26 | Sprint 2 | Ed | Steve | Closed | FALSE | TRUE | 1 | 0 | 0 |  | dev
59 | Enter CI license info. on Server |  | 26 | Sprint 2 | Ed | Steve | Closed | FALSE | TRUE | 1 | 13 | 0 |  | dev
60 | Configure CI on Travis-CI website |  | 26 | Sprint 2 | Ed | Steve | Closed | FALSE | TRUE | 1 | 2 | 0 |  | dev
61 | Add UI functionality to select one or more types |  | 34 |  | Ed | Steven | In progress | FALSE | FALSE | 1 | 0 | 0 |  | dev
62 | Modify query to incorporate type criteria |  | 34 |  | Ed | Ed | New | FALSE | FALSE | 1 | 0 | 0 |  | dev
63 | Complete research of AWS monitoring capability |  | 26 | Sprint 2 | Ed | Ed | Closed | FALSE | TRUE | 1 | 15 | 0 |  | dev
64 | Implement standard error server response |  | 26 | Sprint 2 | Ed | Ed | Closed | FALSE | TRUE | 1 | 12 | 0 |  | dev
65 | Implement standard client error display |  | 26 | Sprint 2 | Ed | Steven | Closed | FALSE | TRUE | 1 | 18 | 0 |  | dev
66 | Standardize Unit Testing approach |  | 26 | Sprint 2 | Ed | Steven | Closed | FALSE | TRUE | 1 | 16 | 0 |  | dev
67 | Implement basic continuous monitoring via AWS |  | 26 | Sprint 2 | Ed | Ed | Closed | FALSE | TRUE | 1 | 6 | 0 |  | dev
69 | Download and Set Up OpenSource Test Management Tool |  | 26 | Sprint 2 | David | David | Closed | FALSE | TRUE | 1 | 17 | 0
70 | Create Manual Funtional Test Case for acceptance Criteria |  | 26 | Sprint 2 | David | David | Closed | FALSE | TRUE | 1 | 8 | 0
71 | Add UI Functioanlity for More button |  | 25 | Sprint 3 | Steven | Steven | Closed | FALSE | TRUE | 1 | 1 | 0 |  | dev
73 | Execute Functional Test Case |  | 26 | Sprint 2 | David | David | Closed | FALSE | TRUE | 1 | 1 | 0
74 | Create Functional Test Case Scenario |  | 34 |  | David | David | Closed | FALSE | TRUE | 1 | 0 | 0
75 | Execute Functional Test Case |  | 34 |  | David |  | New | FALSE | FALSE | 1 | 1 | 0
76 | Execute Functional Test Case |  | 26 | Sprint 2 | David | David | Closed | FALSE | TRUE | 1 | 5 | 0 |  | testqa
77 | Create Functional Test Scenario |  | 25 | Sprint 3 | David | David | Closed | FALSE | TRUE | 1 | 0 | 0 |  | testqa
78 | Execute Functional Test Case |  | 25 | Sprint 3 | David | David | Closed | FALSE | TRUE | 1 | 2 | 0 |  | testqa
79 | Create Functional Test Scenario |  | 72 | Sprint 3 | David | David | Closed | FALSE | TRUE | 1 | 0 | 0 |  | testqa
80 | Execute Functional Test Case |  | 72 | Sprint 3 | David | David | Closed | FALSE | TRUE | 1 | 3 | 0 |  | testqa
84 | Create UI Esri Code for map |  | 72 | Sprint 3 | Steven | Ed | Closed | FALSE | TRUE | 1 | 6 | 0 |  | dev | 20 m
85 | Create UI functionality to show map on page |  | 72 | Sprint 3 | Steven | Ed | Closed | FALSE | TRUE | 1 | 1 | 0 |  | dev
86 | Pagination for grid | moving to another story | 26 | Sprint 2 | Steven |  | Closed | TRUE | TRUE | 1 | 10 | 0
87 | Incorporate dynamic date for previous month |  | 26 | Sprint 2 | Ed | Steven | Closed | FALSE | TRUE | 1 | 4 | 0 |  | dev
89 | add data to report |  | 25 | Sprint 3 | Billie | Steven | Closed | FALSE | TRUE | 1 | 3 | 0 |  | dev
91 | create unit test |  | 72 | Sprint 3 | Billie | Ed | Closed | FALSE | TRUE | 1 | 4 | 0 |  | dev
92 | code review |  | 72 | Sprint 3 | Billie | Ed | Closed | FALSE | TRUE | 1 | 2 | 0 |  | dev
93 | create unit test |  | 25 | Sprint 3 | Billie |  | Closed | FALSE | TRUE | 1 | 5 | 0
94 | code review |  | 25 | Sprint 3 | Billie | Ed | Closed | FALSE | TRUE | 1 | 4 | 0
95 | implement design features |  | 25 | Sprint 3 | Billie |  | Closed | FALSE | TRUE | 1 | 7 | 0
96 | create unit test |  | 30 | Sprint 4 | Billie | Ed | Closed | FALSE | TRUE | 1 | 7 | 0 |  | dev
97 | conduct code review |  | 30 | Sprint 4 | Billie | Steven | Closed | FALSE | TRUE | 1 | 3 | 0
98 | Create funcational test scripts |  | 30 | Sprint 4 | Billie | David | Closed | FALSE | TRUE | 1 | 0 | 0
99 | set up custom icon markers |  | 72 | Sprint 3 | Ed | Ed | Closed | FALSE | TRUE | 1 | 5 | 0 |  | dev
100 | Execute functional test scripts |  | 30 | Sprint 4 | Billie | David | Closed | FALSE | TRUE | 1 | 2 | 0
101 | set up geocoder to find recall locations |  | 72 | Sprint 3 | Ed | Ed | Closed | FALSE | TRUE | 1 | 3 | 0 |  | dev
102 | create feature layer based on locations and add to map |  | 30 | Sprint 4 | Ed | Ed | Closed | FALSE | TRUE | 1 | 1 | 0 |  | dev
103 | identify logic for suppressing multiple markers at a single location |  | 30 | Sprint 4 | Ed | Ed | Closed | FALSE | TRUE | 1 | 4 | 0 |  | dev
105 | update SRS |  | 104 | Sprint 3 | Billie | Billie | Closed | FALSE | TRUE | 1 | 0 | 0 |  | documentation
106 | create High-Level Design document |  | 104 | Sprint 3 | Billie | Tony | Closed | FALSE | TRUE | 1 | 1 | 0 |  | documentation
107 | Modify refiner ui components |  | 90 | Sprint 4 | Steven | Steven | Closed | FALSE | TRUE | 1 | 0 | 0
108 | Add big query text to UI |  | 90 | Sprint 4 | Steven | Steven | Closed | FALSE | TRUE | 1 | 3 | 0
109 | Fix Bootstrap theme / Grunt issue |  | 25 | Sprint 3 | Steven | Steven | Closed | FALSE | TRUE | 1 | 6 | 0
110 | review aws monitoring and system monitoring and provide update | Continuous monitoring metrics will be performed through Amazon cloudwatch. A combination of out of the box metrics and custom application metrics will be continuously monitored. Application metrics which will be added include: Application Up/Down status (alarm when down) Number of page hits Number of errors detected Average Page Get Time (alarm when exceeds threshold) | 104 | Sprint 3 | Billie | Steve | Closed | FALSE | TRUE | 1 | 2 | 0
120 | add design components |  | 28 | Sprint 4 | Billie |  | Closed | FALSE | TRUE | 1 | 6 | 0
121 | unit test |  | 28 | Sprint 4 | Billie |  | Closed | FALSE | TRUE | 1 | 4 | 0
122 | code review |  | 28 | Sprint 4 | Billie | Ed | Closed | FALSE | TRUE | 1 | 3 | 0 |  | dev
123 | Create Functional Test Scenario |  | 28 | Sprint 4 | Billie | David | Closed | FALSE | TRUE | 1 | 8 | 0
124 | Execute Functional Test Case |  | 28 | Sprint 4 | Billie | David | Closed | FALSE | TRUE | 1 | 2 | 0
125 | update documentation with any applicable changes |  | 28 | Sprint 4 | Billie |  | Closed | FALSE | TRUE | 1 | 1 | 0 |  | documentation
126 | add helper text | this was changed to randomizer | 28 | Sprint 4 | Billie | Steven | Closed | FALSE | TRUE | 1 | 5 | 0
127 | Setup controller for binding to search term query |  | 28 | Sprint 4 | Steven | Steven | Closed | FALSE | TRUE | 1 | 9 | 0
128 | Swap in corn images |  | 117 | Sprint 4 | Ed | Ed | Closed | FALSE | TRUE | 1 | 0 | 0 |  | dev
129 | update food label to corn color |  | 117 | Sprint 4 | Ed | Steven | Closed | FALSE | TRUE | 1 | 1 | 0 |  | dev
130 | Enable morgan application logging in application |  | 112 | Sprint 5 | Steve | Steve | Closed | FALSE | TRUE | 1 | 3 | 0
131 | Connect to AWS metrics console for production server |  | 112 | Sprint 5 | Steve | Steve | Closed | FALSE | TRUE | 1 | 0 | 0
132 | Add AWS out of the box metrics/alarms for production server |  | 112 | Sprint 5 | Steve | Steve | Closed | FALSE | TRUE | 1 | 1 | 0
133 | Add custom metrics for AWS monitoring |  | 112 | Sprint 5 | Steve | Steve | Closed | FALSE | TRUE | 1 | 2 | 0
134 | add header |  | 119 | Sprint 4 | Billie | Steven | Closed | FALSE | TRUE | 1 | 0 | 0
135 | test |  | 119 | Sprint 4 | Billie |  | Closed | FALSE | TRUE | 1 | 1 | 0
136 | add api code for SEARCH param |  | 90 | Sprint 4 | Steven | Steven | Closed | FALSE | TRUE | 1 | 6 | 0
137 | Create Functional Test Scenario |  | 90 | Sprint 4 | Billie | David | Closed | FALSE | TRUE | 1 | 1 | 0 |  | testqa
138 | unit test |  | 90 | Sprint 4 | Billie | Steven | Closed | FALSE | TRUE | 1 | 4 | 0
139 | code review |  | 90 | Sprint 4 | Billie | Ed | Closed | FALSE | TRUE | 1 | 2 | 0 |  | dev
140 | Execute Test Case |  | 90 | Sprint 4 | Billie | David | Closed | FALSE | TRUE | 1 | 5 | 0 |  | testqa
141 | Use module scope var for resultset |  | 30 | Sprint 4 | Ed | Ed | Closed | FALSE | TRUE | 1 | 6 | 0 |  | dev
142 | Move map refresh code into function |  | 30 | Sprint 4 | Ed | Ed | Closed | FALSE | TRUE | 1 | 5 | 0 |  | dev
144 | write unit test |  | 111 | Sprint 5 | Billie | Steven | Closed | FALSE | TRUE | 1 | 3 | 0
146 | Create Location parsing |  | 45 | Sprint 5 | Steven | Steven | Closed | FALSE | TRUE | 1 | 4 | 0 |  |  | 0.5
147 | Retrieve location data from module scope |  | 45 | Sprint 5 | Ed | Ed | Closed | FALSE | TRUE | 1 | 6 | 0 |  | dev
148 | Geocode dictionary of locations |  | 45 | Sprint 5 | Ed | Ed | Closed | FALSE | TRUE | 1 | 5 | 0 |  | dev
149 | create unit test |  | 45 | Sprint 5 | Billie | Ed | Closed | FALSE | TRUE | 1 | 2 | 0 |  | dev
150 | code review |  | 45 | Sprint 5 | Billie | Steven | Closed | FALSE | TRUE | 1 | 1 | 0 |  | dev
151 | Create Functional Test Case |  | 45 | Sprint 5 | Billie | David | Closed | FALSE | TRUE | 1 | 9 | 0 |  | testqa
152 | Switch to drug icon when drug recalls are selected |  | 82 | Sprint 5 | Ed | Ed | Closed | FALSE | TRUE | 1 | 4 | 0 |  | dev
153 | Verify location naming conventions for parsing |  | 45 | Sprint 5 | Steven | Steven | Closed | FALSE | TRUE | 1 | 0 | 0 |  |  | 0.5
154 | Create sized bubbles for each area based on value |  | 45 | Sprint 5 | Ed | Ed | Closed | FALSE | TRUE | 1 | 3 | 0 |  | dev
155 | Create separate API call for Device search |  | 83 | Sprint 5 | Ed | Steven | Closed | FALSE | TRUE | 1 | 0 | 0 |  | dev
156 | Create separate API call for Drug search |  | 82 | Sprint 5 | Ed | Steven | Closed | FALSE | TRUE | 1 | 2 | 0 |  | dev
157 | Adjust styles/cols for better fit and look of cols |  | 33 | Sprint 5 | Steven | Steven | Closed | FALSE | TRUE | 1 | 0 | 0
158 | Incorporate Drug image |  | 82 | Sprint 5 | Ed |  | Closed | FALSE | TRUE | 1 | 5 | 0 |  | dev
159 | Incorporatae Device image |  | 83 | Sprint 5 | Ed |  | Closed | FALSE | TRUE | 1 | 5 | 0 |  | dev
160 | create unit test |  | 82 | Sprint 5 | Billie | Steven | Closed | FALSE | TRUE | 1 | 8 | 0
161 | code review |  | 82 | Sprint 5 | Billie | Ed | Closed | FALSE | TRUE | 1 | 3 | 0 |  | dev
162 | update docs |  | 82 | Sprint 5 | Billie |  | Closed | FALSE | TRUE | 1 | 9 | 0
163 | C |  | 82 | Sprint 5 | Billie |  | Closed | FALSE | TRUE | 1 | 7 | 0
164 | Execute Test Case |  | 82 | Sprint 5 | Billie | David | Closed | FALSE | TRUE | 1 | 0 | 0 |  | testqa
165 | Create additional client side handler |  | 82 | Sprint 5 | Steven | Steven | Closed | FALSE | TRUE | 1 | 0 | 0 |  |  | 1
166 | Modify dependencies such as Randomizer list |  | 82 | Sprint 5 | Steven | Steven | Closed | FALSE | TRUE | 1 | 10 | 0 |  |  | 0.5
167 | unit test |  | 33 | Sprint 5 | Billie |  | Closed | FALSE | TRUE | 1 | 3 | 0
168 | code review |  | 33 | Sprint 5 | Billie |  | Closed | FALSE | TRUE | 1 | 5 | 0
169 | Create Functional Test Scenario |  | 33 | Sprint 5 | Billie | David | Closed | FALSE | TRUE | 1 | 4 | 0 |  | testqa
170 | Execute Test Case |  | 33 | Sprint 5 | Billie | David | Closed | FALSE | TRUE | 1 | 2 | 0 |  | testqa
171 | update docs |  | 33 | Sprint 5 | Billie |  | Closed | FALSE | TRUE | 1 | 1 | 0
172 | Create dynamic search term binding |  | 188 | Sprint 5 | Steven | Steven | Closed | FALSE | TRUE | 1 | 1 | 0
173 | Create Functional Test Scenario |  | 111 | Sprint 5 | Billie | David | Closed | FALSE | TRUE | 1 | 1 | 0 |  | testqa
174 | Execute Test Case |  | 111 | Sprint 5 | Billie | David | Closed | FALSE | TRUE | 1 | 0 | 0 |  | testqa
175 | update docs |  | 111 | Sprint 5 | Billie |  | Closed | FALSE | TRUE | 1 | 2 | 0
176 | create unit test |  | 83 | Sprint 5 | Billie | Steven | Closed | FALSE | TRUE | 1 | 2 | 0
177 | code review |  | 83 | Sprint 5 | Billie |  | Closed | FALSE | TRUE | 1 | 4 | 0
178 | update docs |  | 83 | Sprint 5 | Billie |  | Closed | FALSE | TRUE | 1 | 7 | 0
179 | Create Functional Test Case |  | 83 | Sprint 5 | Billie | David | Closed | FALSE | TRUE | 1 | 6 | 0 |  | testqa
180 | Execute Test Case |  | 83 | Sprint 5 | Billie | David | Closed | FALSE | TRUE | 1 | 0 | 0 |  | testqa
181 | add content with correct style |  | 111 | Sprint 5 | Steven | Steven | Closed | FALSE | TRUE | 1 | 0 | 0
182 | Install aws CLI on production server |  | 143 | Sprint 5 | Steve | Steve | Closed | FALSE | TRUE | 1 | 0 | 0
183 | Register custom collected metrics into Amazon cloudworks via CLI calls |  | 143 | Sprint 5 | Steve | Steve | Closed | FALSE | TRUE | 1 | 1 | 0
184 | Create AWS alarms on custom metrics |  | 143 | Sprint 5 | Steve | Steve | Closed | FALSE | TRUE | 1 | 3 | 0
185 | Research other APIs |  | 188 | Sprint 5 | Steven | Steve | Closed | FALSE | TRUE | 1 | 0 | 0
186 | Implement popup on icons |  | 45 | Sprint 5 | Ed | Ed | Closed | FALSE | TRUE | 1 | 7 | 0 |  | dev
187 | Implement auto-resize based on featurelayer boundary |  | 45 | Sprint 5 | Ed | Ed | Closed | FALSE | TRUE | 1 | 8 | 0 |  | dev
189 | unit test |  | 188 | Sprint 5 | Billie |  | Closed | FALSE | TRUE | 1 | 2 | 0
190 | code review |  | 188 | Sprint 5 | Billie |  | Closed | FALSE | TRUE | 1 | 3 | 0
191 | Create Functional Test Case |  | 188 | Sprint 5 | Billie | David | Closed | FALSE | TRUE | 1 | 5 | 0 |  | testqa
192 | Execute Test Case |  | 188 | Sprint 5 | Billie | David | Closed | FALSE | TRUE | 1 | 0 | 0 |  | testqa
193 | Execute Functional Test Case |  | 45 | Sprint 5 | David | David | Closed | FALSE | TRUE | 1 | 2 | 0 |  | testqa
194 | Create Functional Test Scenario |  | 82 | Sprint 5 | David | David | Closed | FALSE | TRUE | 1 | 6 | 0 |  | testqa
195 | integrate api |  | 188 | Sprint 5 | Billie | Steven | Closed | FALSE | TRUE | 1 | 6 | 0 |  | dev
196 | Switch to device icon for device recall searches |  | 83 | Sprint 5 | Ed | Ed | Closed | FALSE | TRUE | 1 | 3 | 0 |  | dev
197 | Check in continuous integration and continuous monitoring scripts (external to app build) |  | 143 | Sprint 5 | Steve | Steve | Closed | FALSE | TRUE | 1 | 2 | 0
221 | implement update |  | 212 | Sprint 6 - Release Sprint | Billie | Ed | Closed | FALSE | TRUE | 1 | 2 | 0 |  | dev
222 | update unit tests |  | 212 | Sprint 6 - Release Sprint | Billie | Ed | Closed | FALSE | TRUE | 1 | 1 | 0 |  | dev
223 | update docs |  | 212 | Sprint 6 - Release Sprint | Billie |  | Closed | FALSE | TRUE | 1 | 1 | 0
224 | Create Functional Test Case |  | 212 | Sprint 6 - Release Sprint | Billie | David | Closed | FALSE | TRUE | 1 | 0 | 0
225 | implement update |  | 211 | Sprint 6 - Release Sprint | Billie | Steven | Closed | FALSE | TRUE | 1 | 1 | 0
226 | update unit tests |  | 211 | Sprint 6 - Release Sprint | Billie | Steven | Closed | FALSE | TRUE | 1 | 0 | 0
227 | update docs |  | 211 | Sprint 6 - Release Sprint | Billie |  | Closed | FALSE | TRUE | 1 | 0 | 0
228 | test |  | 211 | Sprint 6 - Release Sprint | Billie | David | Closed | FALSE | TRUE | 1 | 1 | 0
232 | Execute Functional Test Case |  | 212 | Sprint 6 - Release Sprint | David | David | Closed | FALSE | TRUE | 1 | 1 | 0
237 | Remove old Affected Area refine |  | 236 | Sprint 7 | Steven | Steven | Closed | FALSE | TRUE | 1 | 2 | 0
238 | Fix bug associated with date query |  | 236 | Sprint 7 | Steven | Steven | Closed | FALSE | TRUE | 1 | 3 | 0
239 | Update navbar Defender button reset functionality with new map refiner |  | 236 | Sprint 7 | Steven | Steven | Closed | FALSE | TRUE | 1 | 6 | 0
240 | Remove "-" from big query text |  | 236 | Sprint 7 | Steven | Steven | Closed | FALSE | TRUE | 1 | 4 | 0
241 | Add warning to about section regarding Google Trends limit |  | 236 | Sprint 7 | Steven | Steven | Closed | FALSE | TRUE | 1 | 5 | 0
242 | Fix for google trends Error-500 issue | This is what you get when you navigate directly to one of those problematic Top Region searches, http://www.google.com/trends/fetchComponent?q=asdfz&cid=GEO_TABLE_0_0&export=3&h=200 What's happening is that IE is allowing an iframe that returns 500 to display. In Chrome, the apparent behavior is to not "refresh" the iframe. That's why it appears to not break in Chrome. If you search for "asdfz" on our site using Chrome after just loading up the page, you can see in the Top Regions that it still says "Show results for food-recall" while the others show "asdfz". This is on google's end. Handling this type of error on our end would take a good chunk of time. | 236 | Sprint 7 | Steven | Steven | Closed | FALSE | TRUE | 1 | 0 | 0
243 | Regression Testing |  | 236 | Sprint 7 | David | David | Closed | FALSE | TRUE | 1 | 1 | 0